# Development of Catalysts for Increasing Soybean Oil Content in Renewable Coatings

PI: Alexander Rene Parent

## Research Objectives

  - Measure the drying ability of commercial cobalt and iron-based driers with soybean oil.

  - Characterize the structural properties of cobalt and iron-based driers that enhance the properties of soybean oil-based coatings.

  - Design cobalt and iron-based driers optimized for use with soybean oil.

## Completed Work

We have successfully developed an SOP for characterizing the drying of soybean oil using cobalt driers via FTIR in a reproducible manner. We have also measured the rates of soybean oil autoxidation using Co(hfac)2 at 1.36, 2.04, and 2.72 mM concentrations, and Co(acac)2 at 2.04 mM concentration as part of research objective a). We have also begun synthesis on TPA and bispidine ligand scaffolds for the synthesis of Co and Fe driers with well-defined electronic properties to begin working on research objective b).

## Preliminary Results

Based on our current data, soybean oil autoxidation currently obeys the same mechanism as linseed oil autoxidation and can thus be modeled using our previously developed SOP for linseed oil. Analysis of the initial rates of soybean oil autoxidation using our model demonstrates that higher concentrations of the drier lead to enhanced autoxidation rates, in line with our expectations. While autoxidation of the soybean oil is overall slower than what we saw in our previous work on linseed oil, we have observed maximum reactivity in soybean oil under different conditions that were optimal for linseed oil. We had previously found that linseed oil autoxidation is fastest using 2.04 mM Co(hfac)2, but our new results show soybean oil autoxidation is fastest when using 2.72 mM Co(hfac)2. This is extremely promising for our overall objective of designing driers specifically tailored to soybean oil.

### Work to be Completed

We initially expected to have completed our work on research objective one by the end of August, however we ran into unexpected difficulties finding reproducible conditions for measuring the autoxidation of soybean oil. Specifically, we experienced difficulties setting up and securing reliable power to our FTIR in our new science building, as well as unexpected challenges securing a reliable source of high-quality soybean oil. Due to these challenges, we were unable to finalize an SOP for studying the autoxidation of soybean oil until mid-October, when the power issues in the building were finally resolved. Since October, we have collected data for 4 out of the proposed 12 reaction conditions in the MOU, with each datapoint collected in triplicate to ensure reproducibility and anticipate collecting data for the remaining reaction conditions by the end of 2022.

In order to compensate for the delays in objective a), we began synthesizing ligands for use in objective b) concurrently in September, and currently have four different TPA ready for synthesizing Co and Fe complexes. We also have all the supplies for synthesizing the bispidine complexes in hand, and will be able to synthesize bispidine-based driers as soon as we clear our backlog of driers queued up from objective a). We are also preparing to begin characterizing the physical properties of coatings formed from soybean oil using these driers in early 2023. These physical properties will then be correlated with the mechanistic studies to design complexes for use in research objective c).