FY 2023 Mid-Year Report ND Soybean Council

Pigweed Awareness Coalition: Increasing Awareness and Risk of Palmer amaranth and Waterhemp in ND

Objectives of the research:

This project will provide new Extension programming for Palmer amaranth and waterhemp across North Dakota over the winter of 2022 and 2023. We will record new videos for biology, ID, and management of Palmer amaranth to be used throughout winter meetings. Relevant publications will be created, revised, and/or printed. New information will be presented at winter meetings throughout North Dakota, including new audiences like the Stockman’s Association. The goal will be to ensure all audiences are informed on the risks that Palmer amaranth and waterhemp pose to crop production in North Dakota

Completed work:

Five Palmer amaranth videos were recorded and edited in August-October. These are available for use within Extension and externally for commodity groups or others. Information and publications were sent to the Stockman’s Association meeting in October.

Several radio interviews have been conducted as of December 1 2022 to highlight some of the important objectives of the campaign.

Preliminary results:

Work to be completed:

Results from 2022 field and greenhouse trials are being analyzed and summarized in December 2022.

Two to three updated noxious weed publications with additional Palmer amaranth information are being updated in early 2023.

Additional Powerpoint presentations will be built and recorded for Agents to use in private pesticide recertification trainings in Q1 2023. Presentation materials will also be presented at commercial applicator trainings over the same period. It is estimated that over 10,000 applicators, advisors, agronomists, etc will be exposed to these new research results and materials throughout Q1 of 2023 at NDSU Extension meetings.