Progress Report

Project Proposal – How are methionine absorption and gut barrier function affected by soybean meal-induced enteritis in salmonids, and what are the roles of specific anti-nutritional factors?

Proposal Information

Principal Investigator name: Dr. Brian C. Small

Co-principal Investigator name: Dr. Madison S. Powell

Post-Doctoral Fellow name: Dr. Marina Subramaniam

Organization: University of Idaho – Hagerman Fish Culture Experiment Station

Start Date: May 1, 2024

Completion Date: April 30, 2026

Species: Atlantic Salmon (Salmo salar) and Rainbow Trout (Oncorhynchus mykiss)

Project Goal

This proposal will focus on project priority number II: understand and reduce anti-nutritional factors of soy in aquaculture. Specifically, we will be investigating the intestinal absorption of methionine and gut barrier function in response to soybean meal-induced enteritis (SBMIE) from soybean meal-based (SBM) diets compared with fishmeal-based diets and assess the effects of specific anti-nutritional factors in Atlantic salmon and rainbow trout.

Progress Summary

| Year 1 – Objective 1 |  |  |  | Year 2 – Objectives 2 and 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Baseline characterization | 12-week feeding trial |  |  | Ussing chamber characterization of methionine transport and gut barrier function with diets and ANFs |  |  | Gene expression analysis |

Year 1 – Objective 1:

We have completed the purchase of the Ussing chamber (7/8/2024) and are in the process of its setup and calibration. This includes setting up the software and accessory equipment, as well as conducting preliminary experiments on trout intestinal tissues. These preliminary experiments will be cross-referenced with previously published research with Ussing chambers in trout to ensure accuracy of results and proper functioning of this machine. All chemicals (i.e.: physiological buffer components, isotope, etc.) and accessory equipment (i.e.: gas tanks, water bath chillers, etc.) required for the Ussing chambers have been purchased to establish baseline characterization of methionine transport in both salmon and trout. During the measurements of methionine transport, flux samples taken from the Ussing chamber will be measured on a liquid chromatography-mass spectrometry instrument (LC-MS). The facility required to perform the LC-MS measurements has been set up, with a technician present to help with its troubleshooting and analysis. Finally, we have been growing trout and salmon to an acceptable size (~300-400g) for the Ussing chambers to complete baseline characterization experiments. Intestinal tissue samples will be collected and frozen (-80oC) for gene expression analysis for Year 2 – Q4.