NCSRP

Management Tactics and Tools for Insect Pests in the North Central Region

1. Soybean Gall Midge (SGM) Management

A. Early Warning System & Pest Detection

- Sites for the 2025 season have been selected.

- Protocols finalized for stem burial studies, leveraging NE data and regional input.

- Alert Network expanded to a total of 630 subscribers across 8 Midwestern states and 2 Canadian provinces. Some participants are resubscribing each year, highlighting the system's continued value to their operation.

- Pheromone selection protocols established; early data supports improved adult detection potential.

B. Resistant Varieties

- NE, IA, and SD are coordinating a detailed data collection on 20 elite lines; NE will test 25 more lines in less detail. Crossing will begin this year on resistant lines to start the process of identifying resistant genes.

- An additional MN-funded project with Dr. Koch allows testing soybean lines under controlled conditions

- NE will conduct an additional semi-field study for further insights.

C. Optimized Insecticide Use

- Unified protocol set by NE, IA, and SD, with coordination ahead of full-scale data collection.

- Preliminary 2024 data shows promise.

- NE will test a drop nozzle treatment and implement hilling as a positive control.

2. Soybean Tentiform Leafminer

- Field survey protocol developed with collaborator feedback.

- Dr. Koch will lead a scouting and ID session in August prior to survey implementation.

- NE had its first detection of tentiform leafminer in Sept. of 2024 in Madison County.

3. Soybean Aphid Resistance & Management

- Experimental design and procedures complete.

- Seed procurement coordinated with Corteva for upcoming planting.

4. Awareness & Needs Assessment (Year 2 Only Project - Fall 2025 Launch)

- Planning meetings underway to designate an evaluation expert.

- An initial framework was developed for impact and needs assessment strategy, including focus group settings.

5. Dectes Stem Borer Management

- Team meetings were held to finalize experimental logistics.

- Seeds and chemicals have been secured.

- Some evaluation strategies are focusing on innovative, scalable tools for girdling risk assessment of the Dectes stem borer.

6. Suction Trap Network for Pest Monitoring

- Supplies were distributed to participants.

- Data from prior years is under analysis; the manuscript focused on thrips is in progress.

- Initial modeling efforts on aphid data have begun.

7. Extension and Outreach

- The development of a Soybean Gall Midge Field Guide is underway with assigned contributors and a structured outline.

- We plan to distribute the field guide through SRIIN and hard copy throughout the region with a focus on areas that are currently under threat.

- The annual SGM webinar (Feb 2025) drew 284 registrants, 178 live attendees, and over 40 written questions, highlighting ongoing stakeholder engagement and research interest.