| ## Project Number: | 44215 |
| --- | --- |
| ## Project Title: | Implementing integrated approaches to select for feed efficient rainbow trout families to enhance the soy protein utilization in salmonid aquaculture |
| ## Organization: | University of Idaho |
| ## Project Lead Name: | Brian Small (PI); Vikas Kumar (coPI); Ken Overturf (coPI) |
| ## Report Date: | May 29, 2025 |
| ## Project Summary: ## Overview of project in non-proprietary lay language suitable to be shared publicly. |  |
| Aquaculture provides sustainable production of food fish with high protein/low-saturated fat to satisfy increasing demand. Globally, efficient and environmentally sustainable aquaculture production systems are urgently required. Over two decades of selective breeding, our research resulted in development of a rainbow trout strain that grows as well on an all-plant protein diet as on a fishmeal-based diet, and grows much faster than non-selected trout. Feed accounts for over 60% of the cost of aquaculture production. To date, no commercial breeding programs have selected for improved feed utilization efficiency in fish, mainly because of the difficulty in accurately measuring individual feed intake of fish reared in groups. Therefore, for this project, we will develop an indirect benchmark to use in selecting trout for improved feed utilization efficiency of soy protein protein-based diets, with the long-term goal of reducing the cost of producing commercial trout. Results of each objective will be compared and validated for feed efficient trout lines. Currently, major commercial trout producers, providing a pipeline for transferring our findings directly to stakeholders, are using our selected trout lines. Overall, successful selection for improve feed efficiency will have a broad application to commercial fish selective breeding programs, leading to increased profitability for US farmers. |  |
| ## Detailed Project Status: Expand upon the above section. What key activities were undertaken and what were the key accomplishments during this reporting period? List each key deliverable from the proposal and describe progress made (or not made) toward achieving it, including metrics where appropriate. |  |
| Objectives 1 and 2 have been completed. Two studies to establish an indirect set of benchmarks to be used in selection of rainbow trout to enhance the efficiency of growth and utilization of plant protein-based diets were performed. The first was based on the incorporation of isotopically labeled amino acids by trout from the feed as an indirect measure of protein efficiency. The second was a fed-fast study to measure residual feed intake in trout. For both studies, the fish were statistically separated into performance quartiles, with high and low performing fish selected for breeding this fall. The offspring will be evaluated in the spring of 2025 for performance on high soy feeds and used to estimate the potential genetic gain towards the utilization of soybean meal-based diets (SBMD) in terms of growth performance and feed efficiency (Objective 3). During the fall 2024 spawning season, twelve crosses were generated from the families categorized for growth and isotope retention in the SAA study. These crosses consisted of 4 high x high crosses (retention/growth), 4 low x low crosses, 2 average by average crosses and 2 high x low crosses utilizing alternative high and low males and females. Eggs were hatched and reared for the feeding trial with families of trout representing all crosses. The first week of April, fish were be stocked into tanks for the final feeding trial, where they are being fed a high-soy diet with growth and feed efficiency evaluated over 12 weeks. These results will be used to complete Objective 3, quantifying the genetic potential gain of fish via calculating heritability towards the utilization of SBMD in terms of growth performance and feed efficiency. Everything is on-track for completion by the project end date. |  |